## Matter
Task | Total Test Cases | Automatable | Test cases Count for Automation |  | Status | Comment
|  |  | Scripting | Validation
Scripting of Manual test cases for OS layer | 210 |  |  |  | Completed
Implemented screen comparison code |  |  |  |  | Completed | It is using screen verification scenario's
Non-Matter Life Test (adb commands only) | 13 | 13 | 13 | 13 | Completed | Script used for continous run
Non-Matter Life Test with Appium | 13 | 13 | 13 | 13 | Completed | Continuous run was stopped at the middle of the run, so we tried to run withdifferent approach.
Non-Matter Life Test with Appium by using reboot | 13 | 13 | 13 | 13 | Completed | Continuous run was stopped at the middle of the run, so we tried to add reboot after each cycle.
Implemented functions to read xml file - get text by resource, get text by text, get length of the text, verify text from the screen, click text from the screen. |  |  |  |  | Completed | To read xml file, implemented python script and integrated into Non-Matter Life Test script. Kept run for few cycles and observed OS layer application functionalities.
Non-Matter Life Test without Appium | 13 | 13 | 13 | 13 | Completed | Kept continous run for Non-Matter Life Test with get text by resource, get text by text, get length of the text, verify text from the screen, click text from the screen funcitons in robot framework.
Matter Life Test without Apppium | 13 | 12 | 12 | 12 | Completed | Matter application is not stable due to the Matter Application issues like App crash issue, toggle button issues. SoMatter Life Test kept on hold.
Implemented code to send can siganls through CAN simulator |  |  |  |  | Completed | Completed code implementation to send can data while CAN simulator code dumped into Arduino.So integrated that code into the LIfe Test script and EOL scripts.
Long run for 16 hours | 3 | 3 | 3 | 3 | Completed | 8 Hours Sleep signal. 4 Hours Matter Battery signals. 4 Hours Continous signals except Battery signals.
Degradation Test for Non-Matter | 13 | 13 | 13 | 13 | Completed | Captured time before action and after action, calculated difference time.
Developed .bat file for pushing reports with IMEI |  |  |  |  | Completed | Implemented batch script for executing the robot framework, created a folder in the local system with IMEI number of the connected device, stored the reports into that and pushed those reports into the hardware path (data/).
Implemented code for to get sensor values |  |  |  |  | Completed | to get sensor data and stored into the text file.
Matter Sanity Testcases Development | 120 | 52 | 10 | Pending | Pending | Started scripting, but unable to completed scripting due to matter applicatio issues
EOL for Matter without Appium | 10 | 10 | 10 | 10 | Completed | Written test cases for Bluetooth, Wi-Fi, Dailer, Sensors..etc. Execution is running by reading the xml data with python code , but click actions are due not properly due to the reason of applications issues.
EOL for Matter with co-ordinates | 10 | 10 | 10 | 10 | Completed | Written test cases for Bluetooth, Wi-Fi, Dailer, Sensors..etc Every click action is pergormed by using co-ordinates, but verification part is not implemented.
EOL for Matter with Appium | 10 | 10 | 10 | 10 | Completed | Written test cases for Bluetooth, Wi-Fi, Dailer, Sensors..etc Checking the EOL script in latest build, but again faced double tap issues and resource-id issues.
EOL for Matter without USB | 10 | 10 | 10 | 10 | Completed | Written test cases for Bluetooth, Wi-Fi, Dailer, Sensors..etc Establsihed connection with IP Address (Wi-Fi hotspot) and completed execution, but execution time 3.50 minutes.
EOL for Matter without USB (TCP ) | 10 | 10 | 10 | 10 | Completed | Written test cases for Bluetooth, Wi-Fi, Dailer, Sensors..etc Establsihed connection with TC PIP and completed execution, but execution time 3.50 minutes.
EOL for Matter with screen comparision | 10 | 10 | 10 | 10 | Completed | Written test cases for Bluetooth, Wi-Fi, Dailer, Sensors..etc Establsihed connection with IP Address (Wi-Fi hotspot) and completed execution by using Screen comparison code, reduced execution time upto1:30 minutes.
Parallel Test for Matter EOL | 10 | 10 | 10 | 10 | Completed | Written test cases for Bluetooth, Wi-Fi, Dailer, Sensors..etc Executed same script as the above, imeplemented for multiple devices and ketp run at a time in multiple devices, but it running successful few times only.
Non-Matter sanity test cases development | 220 | 151 | 151 | 151 | Completed | Scripting and validation are completed, review also completed. But the toal script is not working because there is latest updates in the application.
Matter Sanity Testcases Development | 120 | 52 | 52 | Pending | Pending | Scripting was completed, validation is pending due to Matter Application issues. Review also pending.
Implementing Code to hit the signals for Jindal |  |  |  |  | Completed | Developed JSON file and .dbc files. Tried to hit the signals into JINDAl, but code is not supported, so we have to modify the code.
Get Temperature text and it's value through the report.html |  |  |  |  | Completed | Completed implementation and review.
Jindal - Sanity test cases Scripting | 12 | 9 | 9 | 9 | Pending | Pending due to JINDAL Application is not stable
Long run ANR issue debugging with dev team and modifying the sequence of signals. |  |  |  |  | Completed | Integrated to current running 16 Hours long run script.
Matter Life Test | 13 | 10 | 7 | 7 | Pending | Completed - Network Name, Bluetooth, Wi-Fi, Loaciton, Maps, CAN, Brightness. Pending - Sensor values, Bluetooth companion app. Scripts were failing due to Matter Application issues (Matter App is crashing after 100 iterations - 8 defects raised)
Matter Life Test with Degradation | 13 | 12 | 12 | 12 | Pending | Due to Matter App crash issue, we have not implemented.
Non Matter Life Test with Degradation | 13 | 12 | 12 | 12 | Completed | Completed and integrated to current running Non-Matter Life Test script.
Smoke Test for Matter | 7 | 7 | 7 | 7 | Completed
Smoke Test for Non- Matter | 7 | 7 | 7 | Pending | Pending
Stability of EOL for Matter | 13 | 10 | 10 | 10 | Completed | EOL script is working fine in Current build (PTG_MMW_SVIC-003.1_DEBUG_LAUNCHER_2.1.13_020724) for single device except signals.
Stability of EOL with new MMW App | 13 | 10 | 10 | 10 | Completed | EOL with / without script is wokring fine and calculated total time of execution, assembling , dessembling time.
Implementing code to send signal through WeCAN |  |  |  |  | Completed | Signal data is transmitting intothe Arduino but that data is reciving into the hardware. So we have to work on this....
getting Sensors values of EOL with new MMW App |  |  |  |  | Completed | Getting sensor data and validating the EOL script.
Developing the python script for getting sensors values and storing the values in CSV file |  |  |  |  | Completed | Python script to get sensor data, store it in a CSV file, and push the CSV file to a specific location. The script retrieves the serial number, calculates the MAX and MIN values, and determines the tolerance for Standard_VIC and Assemble_VIC
Jindal Sanity cases - Feasibility check | 41 | 12 | 12 |  | Completed | Completed test script, validation is not yet started.
Validating non-matter Smoke | 8 | 8 | 8 | 8 | Completed | Scripting and validation are completed,but we didn't complete review .
Validating Smoke | 8 | 8 | 8 | 8 | Completed | Scripting and validation are completed,but we didn't complete review .
Degradation Reports analyzation |  |  |  |  | Completed
Data annotation - Removing duplicate images from the project |  |  |  |  | Completed
Japan Demo testing for MCU 5inch and 7inch | 95 |  |  |  | Completed
OS level sanity test cases for Matter board | 151 | 100 | 100 | 100 | Completed | Scripting and validation are completed